## Read Me
M.Tech Construction Cost Estimation – G+5 Academic Building
Purpose | Academic baseline model for quantity take-off, rate analysis, BOQ, cost optimization, sensitivity and schedule-cost integration.
Important | Study rates and several quantities are explicit assumptions for thesis modelling. Replace them with approved drawings, BBS, soil report, current Kanpur/UP quotations/SOR and detailed MEP schedules before treating the estimate as tender/contract value.
Price/tax basis | Rates are model inputs exclusive of GST. GST is added separately in the model for an illustrative taxable construction-service case. Confirm contract-specific GST/ITC treatment before submission.
Core area | 3600 | m²

## Assumptions
Parameter | Value | Basis
Project type | Institutional / academic building | Study assumption
Location | Kanpur, Uttar Pradesh, India | Study assumption
Configuration | G+5 (6 floors) | Study assumption
Footprint | 30 m × 20 m = 600 m²/floor | Study assumption
Total built-up area | 3,600 m² | Derived: 600×6
Floor-to-floor height | 4.0 m | Study assumption
Structural system | RCC moment-resisting frame with isolated footings | Study assumption; preliminary costing only
Foundation | Isolated RCC footings, 30 column locations | Study assumption; requires soil report/design verification
Concrete | M25 structural RCC; M10 PCC | Study assumption
Reinforcement | Fe500D TMT | Study assumption
External walls | 230 mm clay brick masonry | Baseline assumption
Internal partitions | 150 mm masonry; baseline cost model uses equivalent masonry volume | Study assumption
Flooring | Vitrified tile in teaching/office/circulation areas | Study assumption
Plaster | 12 mm internal; 15 mm external | Study assumption
Waterproofing | Terrace + wet areas | Study assumption
Doors/windows | Engineered/flush doors; aluminium glazed windows | Study assumption
MEP | Plumbing/sanitary and electrical as provisional-sum packages | Study assumption; detailed design needed
Construction duration | 18 months | Study assumption for cash-flow model
Price basis | Academic baseline using explicit study rates; validate with current Kanpur quotations/UP SOR before submission | Methodological rule
GST treatment | 18% added separately to taxable construction-service subtotal for the illustrative model; actual tax treatment must be confirmed for contract structure | Tax assumption; CBIC source governs
Contingency | 3% of direct work cost | Study assumption
Site/project overhead | 8% of direct work cost | Study assumption
Contractor profit | 10% of direct + overhead + contingency | Study assumption

## Quantity_Takeoff
Group | Item | Unit | Quantity | Calculation/Basis
Earthwork | Excavation in foundation pits/trenches | m³ | 319.2 | 30 pits + allowance for grade/services; 60 m³ is explicit provisional allowance
Foundation | PCC M10 below footings | m³ | 12 | 30 footings × 2.0×2.0×0.10
RCC | Footings | m³ | 43.74 | 30 × 1.8×1.8×0.45
RCC | Pedestals | m³ | 4.86 | 30 × 0.6×0.6×0.45
RCC | Columns | m³ | 97.2 | 30 columns × 0.30×0.45×24 m
RCC | Beams including plinth beam | m³ | 255.15 | 270 m beam length/level × 6 suspended levels + plinth beam
RCC | Slabs | m³ | 540 | 600 m² × 150 mm × 6 suspended levels
RCC | Staircases | m³ | 16.875 | Preliminary geometric take-off for 2 stair cores; detailed stair drawing to replace
RCC | Lintels/sunshades/misc. | m³ | 20 | Provisional geometric allowance pending architectural schedule
Reinforcement | TMT reinforcement | t | 107.5607 | 110 kg/m³ of RCC as preliminary costing allowance; replace with bar bending schedule
Masonry | 230 mm/partition masonry equivalent volume | m³ | 891.6 | External wall area 100×24×0.80×0.23 + internal partition equivalent volume
Plastering | Internal wall + ceiling plaster | m² | 13440 | Wall surfaces 9,840 + ceiling 3,600
Plastering | External plaster | m² | 1920 | External wall area after 20% opening deduction
Flooring | Floor finish | m² | 3600 | Built-up area
Flooring | Skirting | m | 1200 | Preliminary perimeter/internal skirting length
Doors/windows | Doors | m² | 189 | 90 doors × 2.1×1.0
Doors/windows | Windows | m² | 225 | 100 windows × 1.5×1.5
Waterproofing | Terrace + wet areas | m² | 1200 | 600 terrace + 600 wet-area allowance
Painting | Internal painting | m² | 13440 | Same treated surface as internal plaster
Painting | External painting | m² | 1920 | Same treated surface as external plaster
External works | Paved area | m² | 1000 | Site circulation/plaza assumption
External works | Storm-water drain | m | 250 | Site drainage assumption

## Rate_Analysis
Item | Unit | Material | Labour | Equipment | Transport/handling | Wastage | Direct build-up | Overheads | Profit | Final unit rate
Excavation | m³ | 0 | 160 | 60 | 15 | 0 | 235 | 11.75 | 7.4 | 254.15
PCC M10 | m³ | 4700 | 850 | 250 | 250 | 150 | 6200 | 310 | 195.3 | 6705.3
RCC M25 | m³ | 6000 | 900 | 450 | 350 | 180 | 7880 | 394 | 248.22 | 8522.22
Reinforcement Fe500D | t | 72000 | 2000 | 500 | 500 | 720 | 75720 | 3786 | 2385.18 | 81891.18
Masonry | m³ | 6400 | 1200 | 100 | 300 | 150 | 8150 | 407.5 | 256.73 | 8814.23
Internal plaster | m² | 85 | 150 | 15 | 10 | 5 | 265 | 13.25 | 8.35 | 286.6
Vitrified flooring | m² | 850 | 170 | 30 | 30 | 40 | 1120 | 56 | 35.28 | 1211.28
Painting | m² | 115 | 70 | 8 | 7 | 5 | 205 | 10.25 | 6.46 | 221.71
Waterproofing | m² | 500 | 120 | 20 | 20 | 20 | 680 | 34 | 21.42 | 735.42

## BOQ
Sr | Group | Description | Unit | Quantity | Rate | Amount
1 | Earthwork | Excavation in foundation pits/trenches | m³ | 319.2 | 254.15 | 81124.68
2 | Foundation | PCC M10 below footings | m³ | 12 | 6705.3 | 80463.6
3 | RCC | RCC M25 in footings, columns, beams, slabs and stairs | m³ | 977.825 | 8522.22 | 8333239.7715
4 | RCC | Formwork to RCC | m² | 15000 | 900 | 13500000
5 | Reinforcement | TMT reinforcement Fe500D | t | 107.5607 | 81891.18 | 8808276.7392
6 | Masonry | Baseline clay-brick/equivalent masonry | m³ | 891.6 | 8814.23 | 7858767.468
7 | Plastering | Internal plaster | m² | 13440 | 286.6 | 3851904
8 | Plastering | External plaster | m² | 1920 | 365 | 700800
9 | Flooring | Vitrified flooring | m² | 3600 | 1211.28 | 4360608
10 | Flooring | Skirting | m | 1200 | 140 | 168000
11 | Doors/windows | Doors | m² | 189 | 12000 | 2268000
12 | Doors/windows | Windows | m² | 225 | 9000 | 2025000
13 | Waterproofing | Terrace and wet-area waterproofing | m² | 1200 | 735.42 | 882504
14 | Painting | Internal painting | m² | 13440 | 221.71 | 2979782.4
15 | Painting | External painting | m² | 1920 | 250 | 480000
16 | External works | Paving | m² | 1000 | 900 | 900000
17 | External works | Storm-water drain | m | 250 | 1800 | 450000
18 | Services | Plumbing and sanitary package | LS | 1 | 3200000 | 3200000
19 | Services | Electrical and lighting package | LS | 1 | 4800000 | 4800000
20 | External works | Site development/landscape | LS | 1 | 1500000 | 1500000

## Cost_By_Group
Group | Amount | % Direct Cost
Earthwork | 81124.68 | 0.12067
Foundation | 80463.6 | 0.11969
RCC | 21833239.7715 | 32.4762
Reinforcement | 8808276.7392 | 13.102
Masonry | 7858767.468 | 11.6896
Plastering | 4552704 | 6.772
Flooring | 4528608 | 6.7361
Doors/windows | 4293000 | 6.3857
Waterproofing | 882504 | 1.3127
Painting | 3459782.4 | 5.1463
External works | 2850000 | 4.2393
Services | 8000000 | 11.8997

## Resource_Split
Category | Amount | % Direct Cost
Materials | 36975658.8623 | 55
Labour | 16807117.6647 | 25
Equipment/machinery | 4705992.9461 | 7
Specialist/subcontract packages | 8739701.1856 | 13

## Alternatives
Option | Alternative | Relative initial cost* | Relative labour/time* | Technical implication | Decision | Note
Baseline | Clay-brick masonry | 1.00 | 1.00 | Baseline | Reference | Relative factors are study hypotheses for testing; replace with supplier/productivity data before claiming savings.
A1 | AAC block masonry | 0.88 | 0.82 | Lower dead load; faster installation; requires detailing and local availability check | Preferred if structural/seismic and procurement checks pass | Relative factors are study hypotheses for testing; replace with supplier/productivity data before claiming savings.
A2 | Higher-grade concrete only where structurally justified | 0.99 | 0.98 | May reduce member sizes/rebar only after structural redesign; otherwise no automatic saving | Do not adopt merely to reduce cement | Relative factors are study hypotheses for testing; replace with supplier/productivity data before claiming savings.
A3 | Optimized formwork / modular panel system | 0.96 | 0.80 | Higher setup cost but repetitive G+5 geometry can improve cycle time and labour productivity | Potentially attractive for repetitive floors | Relative factors are study hypotheses for testing; replace with supplier/productivity data before claiming savings.
A4 | Flooring substitution: standard vitrified tile | 0.90 | 0.95 | Functionally adequate in most academic areas; verify wear/slip requirements | Good low-risk VE option | Relative factors are study hypotheses for testing; replace with supplier/productivity data before claiming savings.

## Sensitivity
Variable change | Change % | Total project cost | Total cost change %
Steel price | -15 | 95314508.8458 | -1.5971
Steel price | -10 | 95830151.2157 | -1.0647
Steel price | -5 | 96345793.5857 | -0.53235
Steel price | 0 | 96861435.9556 | 0
Steel price | 5 | 97377078.3256 | 0.53235
Steel price | 10 | 97892720.6955 | 1.0647
Steel price | 15 | 98408363.0655 | 1.5971
Labour cost | -15 | 93886576.129 | -3.0713
Labour cost | -10 | 94878196.0712 | -2.0475
Labour cost | -5 | 95869816.0134 | -1.0238
Labour cost | 0 | 96861435.9556 | 0
Labour cost | 5 | 97853055.8978 | 1.0238
Labour cost | 10 | 98844675.8401 | 2.0475
Labour cost | 15 | 99836295.7823 | 3.0713
Cement/concrete input | -15 | 95433503.2388 | -1.4742
Cement/concrete input | -10 | 95909480.8111 | -0.9828
Cement/concrete input | -5 | 96385458.3834 | -0.4914
Cement/concrete input | 0 | 96861435.9556 | 0
Cement/concrete input | 5 | 97337413.5279 | 0.4914
Cement/concrete input | 10 | 97813391.1001 | 0.9828
Cement/concrete input | 15 | 98289368.6724 | 1.4742
Project duration / preliminaries | -15 | 95909480.8111 | -0.9828
Project duration / preliminaries | -10 | 96226799.1926 | -0.6552
Project duration / preliminaries | -5 | 96544117.5741 | -0.3276
Project duration / preliminaries | 0 | 96861435.9556 | 0
Project duration / preliminaries | 5 | 97178754.3371 | 0.3276
Project duration / preliminaries | 10 | 97496072.7186 | 0.6552
Project duration / preliminaries | 15 | 97813391.1001 | 0.9828
Variable | -15% total | Base | +15% total
Steel price | 95314508.8458 | 96861435.9556 | 98408363.0655
Labour cost | 93886576.129 | 96861435.9556 | 99836295.7823
Cement/concrete input | 95433503.2388 | 96861435.9556 | 98289368.6724
Project duration / preliminaries | 95909480.8111 | 96861435.9556 | 97813391.1001

## Schedule_Cashflow
Month | % of pre-GST cost | Monthly expenditure | Cumulative expenditure | Cumulative %
1 | 1.8182 | 1492472.0486 | 1492472.0486 | 1.8182
2 | 2.7273 | 2238708.0729 | 3731180.1216 | 4.5455
3 | 3.6364 | 2984944.0972 | 6716124.2188 | 8.1818
4 | 4.5455 | 3731180.1216 | 10447304.3404 | 12.7273
5 | 5.4545 | 4477416.1459 | 14924720.4862 | 18.1818
6 | 6.3636 | 5223652.1702 | 20148372.6564 | 24.5455
7 | 7.2727 | 5969888.1945 | 26118260.8509 | 31.8182
8 | 8.1818 | 6716124.2188 | 32834385.0697 | 40
9 | 9.0909 | 7462360.2431 | 40296745.3128 | 49.0909
10 | 9.0909 | 7462360.2431 | 47759105.5559 | 58.1818
11 | 9.0909 | 7462360.2431 | 55221465.799 | 67.2727
12 | 8.1818 | 6716124.2188 | 61937590.0178 | 75.4545
13 | 7.2727 | 5969888.1945 | 67907478.2123 | 82.7273
14 | 5.4545 | 4477416.1459 | 72384894.3582 | 88.1818
15 | 4.5455 | 3731180.1216 | 76116074.4798 | 92.7273
16 | 3.6364 | 2984944.0972 | 79101018.577 | 96.3636
17 | 1.8182 | 1492472.0486 | 80593490.6256 | 98.1818
18 | 1.8182 | 1492472.0486 | 82085962.6743 | 100

## Cost_Summary
Built-up area (m²) | 3600
Direct estimated work cost (₹) | 67228470.6587
Site/project overhead @ 8% (₹) | 5378277.6527
Contingency @ 3% of direct cost (₹) | 2016854.1198
Contractor profit @ 10% (₹) | 7462360.2431
Pre-GST project cost (₹) | 82085962.6743
Illustrative GST @ 18% (₹) | 14775473.2814
Illustrative total incl. GST (₹) | 96861435.9556
Illustrative cost per m² incl. GST (₹/m²) | 26905.9544

## Standards_References
Reference | Title / use | Application note
IS 456:2000 | Plain and reinforced concrete – Code of Practice | Structural concrete design/construction basis; current BIS page shows review in 2025.
IS 875 (Part 1):2026 | Dead loads / unit weights | Use current BIS edition for design inputs where applicable.
IS 875 (Part 2):1987 | Imposed loads | Building occupancy loading.
IS 875 (Part 3):2015 | Wind loads | Wind design inputs.
IS 1893 (Part 1):2025 | Design earthquake hazard and criteria – general provisions | Current BIS listing identified in source check; structural designer must apply applicable edition.
IS 10262:2019 | Concrete mix proportioning – Guidelines | Concrete mix design.
IS 383:2016 | Coarse and fine aggregates for concrete | Aggregate specification.
IS 1077:1992 | Common burnt clay building bricks – Specification | Baseline brick masonry material.
IS 2185 Part 3:1984 | Autoclaved cellular concrete blocks | Relevant for AAC alternative.
CPWD DSR 2023 | Delhi Schedule of Rates, Vol I & II | Reference rate nomenclature/rate-analysis structure; use with latest correction slips.
CPWD Analysis of Rates 2023 | Analysis of Rates for Delhi, Vol I & II | Reference for material/labour/equipment build-ups.
CPWD PAR 2025 | Plinth Area Rates 2025 | Benchmark preliminary cost / comparison.
CPWD Building Cost Index 2026 | Delhi BCI dated 01-04-2026 relative to PAR 2025 base | Escalation context only; not a Kanpur location factor.
CPWD Electrical Specifications 2023 | General Specifications for Electrical Works, Part I/II | Electrical specification reference.
CBIC GST | GST rates for construction services | Tax treatment must be mapped to actual contract/project structure.